OSAI

MVP BUILD BRIEF

Competitive Analysis · Open-Source Stack · Build Roadmap

For: Ishika, Anish (CTO), Yash — and the coding agent

May 2026  ·  Confidential

# 1. Executive Summary

This document is a complete technical build brief for OSAI's MVP — intended for the founding team and any coding agent. It synthesises findings from 9 competitor/reference products into a single, actionable spec: what to steal from open-source, what to borrow conceptually from paid products, which repos to fork or compose, and the exact stack to use.

PRIMARY DIRECTIVE: Ship the Meeting Action Item Extractor as a single end-to-end workflow first. Prove the loop works. Then expand the data flywheel. Do not boil the ocean.

# 2. Competitive Landscape

Nine products were analysed — four paid/commercial (Onyx, Glean, Viktor, memory.store) and five open-source (Onyx GitHub, OpenHuman, AIOS, UltraContext, hermes-agent-self-evolution). Below is a summary, followed by per-product deep-dives.

## 2.1 Landscape Map

| Product | Type | Core Bet | Relevant To OSAI |
| --- | --- | --- | --- |
| Onyx | OSS + paid cloud | Enterprise RAG / AI chat over org docs | High — RAG pipeline, connector architecture |
| Glean | Paid enterprise | Enterprise graph + AI assistant + agents | High — positioning, enterprise graph concept |
| Viktor | Paid SaaS | AI coworker living in Slack, executes tasks | High — Slack-native execution model |
| memory.store | Paid SaaS (YC) | Shared memory layer for teams + agents via MCP | High — org brain, MCP pattern |
| OpenHuman | OSS (GPL-3) | Personal AI with persistent memory + Composio integrations | VERY HIGH — closest to OSAI MVP stack |
| AIOS | OSS (research) | LLM OS kernel — schedules agents like OS processes | Medium — agent scheduling inspiration |
| UltraContext | OSS | Context infrastructure for agents — auto-capture context | Medium — context capture pattern |
| hermes-agent-self-evolution | OSS (NousResearch) | DSPy + GEPA agent self-improvement loop | Low for MVP — future prompt optimisation |
| WOZCODE | Paid plugin | Claude Code cost optimiser — 25-50% cheaper | Use now — reduces LLM build cost |

## 2.2 Onyx — Open-Source Enterprise RAG

20k GitHub stars. Python backend (FastAPI), Next.js frontend, PostgreSQL + Vespa/Qdrant for hybrid search. Connectors to 40+ tools (Slack, Notion, Google Drive, Linear, Zoom, etc) via a clean connector interface. Deploys via Docker Compose. MIT licensed for self-host.

### What to steal

- Connector architecture: each integration is a standalone Python class (poll_source, load_credentials, retrieve_docs). Copy this pattern for OSAI's ingestion layer.

- Chunk-level metadata schema: source, doc_id, source_type, time_updated, access_permissions. Use this exact schema for OSAI's Qdrant payloads.

- Access-control filtering at retrieval time: Onyx filters vector search results against user permissions. OSAI needs this for Red/Amber/NA data tiers.

- Agent framework with tool registry: clean separation between tools, agents, and the LLM call. Mirror this for OSAI's workflow engine.

### What to skip

- Vespa (their primary vector store) — you're already on Qdrant, which is better for on-prem and simpler to operate.

- Their full UI — you have your own Next.js shell.

→ GitHub: onyx-dot-app/onyx

→ Connector docs

## 2.3 Glean — Enterprise Graph + Work AI Platform

Paid enterprise product (~$10M+ ARR scale). The most relevant conceptual reference for OSAI's long-term positioning. Glean's architecture is built around two concepts OSAI should adopt:

### Concepts to adopt

- 'System of Context' framing: Glean explicitly positions itself as the context layer that sits above all enterprise tools. This is OSAI's exact positioning — borrow the language.

- Enterprise Graph + Personal Graph: a knowledge graph where entities (people, projects, decisions) are nodes and interactions are edges. For OSAI MVP, this is a future moat — start with flat vector search, but schema towards a graph.

- Agent Governance & Orchestration: Glean has a whole sub-product for managing multiple agents. For MVP, ignore — but design OSAI's agent interface to be composable.

### What's missing from Glean (OSAI's gap to fill)

- Glean has no on-prem LLM support — Red-tier data routing to Ollama is a hard differentiator.

- Glean doesn't do workflow automation — it finds and synthesises. OSAI executes (Linear tickets, approvals).

- Glean is $$$$ for universities and early-stage SaaS — OSAI's pricing is the wedge.

## 2.4 Viktor — AI Coworker in Slack

Slack/Teams-native AI agent. 20k+ workspaces. 3,000+ tool integrations. The key insight: Viktor does not just answer questions — it ships artefacts (PDFs, dashboards, follow-up emails). This is the execution-first framing OSAI needs.

### What to steal

- 'Not a tool. A hire.' — Messaging frame. OSAI should position Meeting Action Item Extractor as: 'Not a note-taker. An executor.'

- Output-first UX: Viktor shows what it produced (PDF attached, tasks created, CRM updated). OSAI's workflow output should surface the artefact (Linear tickets created: 3) not just confirm the run.

- Viktor's 'every conversation makes Viktor smarter about your business' — this is the data flywheel in consumer language.

## 2.5 memory.store — Shared Memory for Teams + Agents (YC P26)

YC-backed. MCP-native. Ingests from Slack, Gmail, Granola, Claude, Codex and builds a shared memory that any agent can read. Very close to OSAI's 'org brain' concept but without the execution layer.

### What to steal

- MCP as the memory interface: expose OSAI's Qdrant index as an MCP server. This lets Cursor, Claude Code, and any future agent tool read org context natively.

- 'Record in Claude, recall in Codex' — the cross-agent memory portability story. OSAI should support this for Anish's engineering workflows immediately.

- 'Organises in the background while your team works' — no new habits. OSAI's Zoom webhook → auto-extract is this pattern.

### Gap vs OSAI

- memory.store has no execution layer — it's a read-only context API. OSAI adds the write side: create tickets, route approvals, send follow-ups.

## 2.6 OpenHuman — OSS Personal AI (GPL-3) ★ PRIMARY REFERENCE

This is the closest open-source equivalent to what OSAI needs to build. 28k stars, 2.6k forks. Written in Rust (backend) + TypeScript (frontend). Composio for integrations. SQLite + Markdown for local memory.

### Architecture (directly reusable)

- Memory Tree: all connected data canonicalised into ≤3k-token Markdown chunks, scored, folded into hierarchical summary trees stored in SQLite. Each chunk also written as .md into an Obsidian-compatible vault.

- Composio connector layer: OAuth + 118+ integrations proxied through Composio. You're already using Composio — OpenHuman's integration patterns are drop-in reference.

- 20-minute auto-fetch scheduler: background loop pulls fresh data from all connected sources. Copy this for OSAI's ingestion refresh cycle.

- LiteLLM abstraction: routes between cloud LLMs and local Ollama. Identical to OSAI's LiteLLM layer.

- Meeting Agent: connects to live Google Meet, captures transcript, generates structured output. This is a v1.1 feature for OSAI.

### What to fork/adapt

- The chunking pipeline (≤3k token chunks with source metadata + temporal scoring)

- The SQLite memory store pattern (simpler than Qdrant for MVP local memory, can migrate later)

- The Composio webhook wiring for real-time triggers

### License note

- GPL-3: you can fork and modify freely for internal use. If you distribute a modified version as a product, you must open-source it under GPL-3 too. For OSAI's SaaS model, you use it as reference architecture, not a direct fork.

→ GitHub: tinyhumansai/openhuman

→ Docs

## 2.7 AIOS — AI Agent Operating System

Academic project from AGI Research (5.6k stars). Treats LLM agents as OS processes — a kernel that schedules agent tasks, manages memory and storage, and provides an agent SDK. Written in Python + Rust.

### What's relevant

- Agent scheduler pattern: OSAI's workflows are essentially async agent tasks. AIOS's scheduler (priority queues, agent memory isolation) is worth studying for when OSAI runs multiple concurrent workflows.

- Storage manager: separates local, memory, and retrieval storage. Maps cleanly onto OSAI's data tier model.

### MVP relevance: LOW. Study for v2 agent orchestration design.

→ GitHub: agiresearch/AIOS

## 2.8 UltraContext — OSS Context Infrastructure

Small repo, focused on auto-capturing and sharing context across agent boundaries. Core idea: context should follow the agent session, not be manually injected.

### What to steal

- Context propagation pattern: when a Zoom meeting triggers OSAI's extractor, the context (meeting title, participants, existing Linear tickets for that project) should be auto-fetched and injected into the LLM call. UltraContext's design formalises this.

→ GitHub: ultracontext/ultracontext

## 2.9 WOZCODE — Claude Code Cost Optimizer

Official Claude Code plugin. Claims 25–50% cost reduction, 5–10x speed improvement. Free tier up to $100/month saved. No signup required.

Install immediately. Run curl -fsSL https://wozcode.com/savings-check.js ¦ node - to check potential savings on existing Claude Code usage. This is a zero-risk tool to reduce build costs from day one.

→ WOZCODE

# 3. What Competitors Are Missing (OSAI's Edge)

| Gap | Glean | Onyx | Viktor | memory.store | OpenHuman | OSAI |
| --- | --- | --- | --- | --- | --- | --- |
| On-prem LLM (Red-tier data) | ✗ | ✗ | ✗ | ✗ | ✓ (partial) | ✓ (Ollama) |
| Workflow execution (tickets, approvals) | ✗ | ✗ | ✓ (Slack only) | ✗ | ✗ | ✓ |
| University/edu vertical | ✓ (enterprise price) | ✗ | ✗ | ✗ | ✗ | ✓ (MU anchor) |
| Zoom webhook → structured action | ✗ | ✗ | ✗ | ✗ | Partial (Meet) | ✓ (MVP v1) |
| Data tier classification (NA/Amber/Red) | ✗ | ✗ | ✗ | ✗ | ✗ | ✓ |
| Approval routing engine | ✗ | ✗ | ✗ | ✗ | ✗ | ✓ (v1.1) |

# 4. MVP Scope — What To Build

MVP = ONE working end-to-end workflow. Not a platform. Not a connector marketplace. One trigger → one extraction → one action output. Everything else is future.

## 4.1 The Single MVP Workflow

Zoom Meeting → Whisper Transcription → LLM Extraction → Linear Tickets via Composio

| Step | Input | Output | Tool |
| --- | --- | --- | --- |
| 1. Trigger | Zoom webhook (meeting ended) | Recording URL + participants | Zoom webhook |
| 2. Transcription | Audio/video URL | Raw transcript text | OpenAI Whisper API |
| 3. Context enrichment | Meeting title + participants | Existing Linear issues, team members | Composio (Linear read) |
| 4. LLM extraction | Transcript + context | JSON: [{title, assignee, priority, due_date}] | LiteLLM → Claude Sonnet |
| 5. Action execution | Extracted action items | Linear tickets created | Composio (Linear write) |
| 6. Confirmation | Created tickets | Slack message with ticket links | Composio (Slack write) |

## 4.2 What Is NOT in MVP v1

- Approval routing engine (v1.1)

- Airbyte ingestion pipeline (replace with direct Composio connectors for MVP)

- Full Qdrant RAG (use SQLite + simple embedding search for MVP, migrate to Qdrant when data volume demands it)

- Multi-workflow support (only Meeting Action Item Extractor)

- Admin UI / settings panel

- Data tier enforcement (build as flag in code, enforce in v1.1)

# 5. Recommended MVP Stack

Stack philosophy: use what OpenHuman proved works (Composio + LiteLLM + SQLite), but keep Qdrant in the architecture for when volume demands it. No Airbyte for MVP — direct Composio connectors are faster to wire.

## 5.1 Backend

| Layer | Tool | Reason | Repo/Link |
| --- | --- | --- | --- |
| API framework | FastAPI (Python) | Same as Onyx — fast, async, excellent LangChain/LiteLLM integration | pip install fastapi |
| LLM abstraction | LiteLLM | Route between Claude Sonnet, GPT-4o, Ollama — one interface | github.com/BerriAI/litellm |
| On-prem LLM | Ollama + Llama 3 / Mistral | Docker Compose, private VPC, Red-tier data isolation | ollama.ai |
| Transcription | OpenAI Whisper API | Fastest path. Self-host Whisper on GPU later for cost. | api.openai.com/v1/audio |
| Embeddings | text-embedding-3-small | Cheap, fast. ~$0.02/1M tokens | OpenAI API |
| Vector DB | Qdrant (Docker) | Already in your stack. Namespace-scoped per org. | qdrant.tech/documentation |
| Memory (MVP) | SQLite via OpenHuman pattern | Zero infra, local-first, matches OpenHuman's battle-tested chunk store | Built-in Python |
| Integrations | Composio | OpenHuman + your existing choice. 118+ integrations, OAuth handled | composio.dev |
| Chunking | LangChain RecursiveCharacterTextSplitter | 512 tokens, 64 overlap, metadata tagging | pip install langchain |
| Task queue | Celery + Redis | Async workflow execution — Zoom webhook fires a Celery task | celeryproject.org |
| Database | PostgreSQL | Store workflow runs, user configs, audit logs | Docker image |

## 5.2 Frontend

| Layer | Tool | Notes |
| --- | --- | --- |
| Framework | Next.js 14 (App Router) | Already your stack. Keep it. |
| Styling | Tailwind CSS | Already your stack. |
| Deployment | Vercel | Already your stack. |
| UI components | shadcn/ui | Drop-in accessible components, zero lock-in |
| State management | Zustand | Lightweight, no Redux complexity for MVP |
| API client | TanStack Query | Handles loading/error states cleanly for workflow status polling |

## 5.3 Infrastructure

| Component | Tool | Notes |
| --- | --- | --- |
| Backend hosting | Railway / Render | Easier than Replit for production. Free tier available. |
| Qdrant | Docker on VPS (Hetzner/DO) | ~$10/mo. Self-host. Or Qdrant Cloud free tier for MVP. |
| Redis | Upstash Redis | Serverless Redis, generous free tier for Celery broker |
| PostgreSQL | Supabase (free tier) | Managed PG + auth layer for free. 500MB is enough for MVP. |
| Ollama (Red tier) | Docker Compose, private VPC | Deploy on pilot client's infra only when needed |
| Secrets | Doppler / .env | Doppler for team, .env for local dev |
| Logging | Logfire (from Pydantic team) | Native FastAPI integration, free tier |

# 6. Open-Source Repos to Use Directly

## 6.1 Must-Use Repos

| Repo | What to use | License | Link |
| --- | --- | --- | --- |
| tinyhumansai/openhuman | Composio wiring patterns, chunk pipeline, SQLite memory store, LiteLLM routing | GPL-3 (reference) | github.com/tinyhumansai/openhuman |
| onyx-dot-app/onyx | Connector interface pattern, chunk metadata schema, access-control filtering at retrieval | MIT ✓ | github.com/onyx-dot-app/onyx |
| BerriAI/litellm | LLM provider abstraction layer — use as pip package | MIT ✓ | github.com/BerriAI/litellm |
| WithWoz/wozcode-plugin | Install as Claude Code plugin to reduce build costs immediately | MIT ✓ | github.com/WithWoz/wozcode-plugin |

## 6.2 Reference-Only Repos (study, don't fork)

| Repo | What to learn | Link |
| --- | --- | --- |
| agiresearch/AIOS | Agent scheduling, multi-agent memory isolation patterns | github.com/agiresearch/AIOS |
| ultracontext/ultracontext | Context propagation between agent invocations | github.com/ultracontext/ultracontext |
| NousResearch/hermes-agent-self-evolution | DSPy prompt optimisation loop — use when OSAI has enough workflow run data | github.com/NousResearch/hermes-agent-self-evolution |

## 6.3 Additional Repos Worth Watching

- composio-dev/composio — official Composio SDK. Use for all integration wiring.

- openai/whisper — self-host Whisper when API costs become significant (>100 meetings/day).

- qdrant/qdrant — read the collections API docs for namespace-scoped per-org indexing.

- celery/celery — webhook → async task pattern. See the 'Canvas' docs for chaining.

# 7. Build Order (for the coding agent)

Each phase must be end-to-end working before the next begins. No half-built layers.

## Phase 0 — Foundation (Day 1–2)

Do once. Infrastructure only.

- Install WOZCODE: curl -fsSL https://wozcode.com/install.sh | bash inside Claude Code session

- Spin up Docker Compose: FastAPI + PostgreSQL + Redis + Qdrant (4 containers, one compose file)

- Wire Composio SDK: install composio-core, authenticate with Composio API key, test Linear connection

- LiteLLM config: create litellm_config.yaml routing claude-sonnet-4-6 (default), gpt-4o (fallback), ollama/llama3 (on_prem)

- Supabase: create tables — orgs, users, workflow_runs, action_items, integrations

## Phase 1 — Webhook Ingestion (Day 3–4)

- FastAPI endpoint: POST /webhooks/zoom — validate Zoom webhook signature, enqueue Celery task

- Celery task: download_and_transcribe(meeting_id) — fetch recording from Zoom API, call Whisper API, store raw transcript in PG

- Test end-to-end: trigger mock Zoom webhook, verify transcript stored in DB

## Phase 2 — LLM Extraction (Day 5–6)

- Context enricher: fetch open Linear issues + team members via Composio before LLM call

- Extraction prompt: system prompt specifying JSON output schema [{title, assignee_email, priority, due_date, context}]. Include meeting context + Linear context.

- LiteLLM call: route to claude-sonnet-4-6 by default. Parse response, validate against Pydantic schema.

- Store extracted items in action_items table with workflow_run_id FK

## Phase 3 — Action Execution (Day 7–8)

- Composio action: create Linear tickets for each extracted action item. Map assignee_email → Linear user ID.

- Composio action: post Slack summary message with ticket links to meeting channel

- Update workflow_runs status: COMPLETED / FAILED with error details

## Phase 4 — UI Surface (Day 9–10)

- Workflow run log page: table of recent runs with status, meeting title, # tickets created, timestamp

- Run detail page: show extracted action items, which were created as tickets, which failed, reason

- Integration setup flow: connect Zoom, Linear, Slack via Composio OAuth — show connection status

- Demo discipline: only show screens that work. Workflow log, run detail, integrations page.

## Phase 5 — Hardening for Pilot (Day 11–14)

- Error handling: dead-letter queue for failed Celery tasks, retry with exponential backoff

- Data tier flag: tag each workflow run as NA/Amber/Red based on org config. Red → force Ollama.

- Org provisioning: create_org() endpoint to onboard MU as first tenant with their Composio credentials

- Basic auth: Supabase Auth with email/password. No SSO yet.

# 8. Data Architecture

## 8.1 Chunking Strategy (from OpenHuman + Onyx)

| Parameter | Value | Rationale |
| --- | --- | --- |
| Chunk size | 512 tokens | Fits most action items + context in one chunk. Onyx default. |
| Overlap | 64 tokens | Preserves sentence boundary context. Standard. |
| Max chunk size | ≤3k tokens | OpenHuman's proven limit for quality retrieval. |
| Format | Markdown | Obsidian-compatible. Human-readable. OpenHuman validated. |
| Metadata | source, doc_id, source_type, time_updated, org_id, data_tier | OSAI additions on top of Onyx schema. |
| Temporal scoring | Recency weight in retrieval | OpenHuman: chunks carry temporal metadata, scored at retrieval. |

## 8.2 Qdrant Collection Design

- One collection per org: collection name = org_{org_id}

- Namespace isolation: each org's vectors are fully separated — no cross-tenant leakage

- Payload fields: { chunk_id, source_type, doc_id, org_id, user_id, data_tier, created_at, content_preview }

- Index: HNSW with ef_construction=100, m=16 — Qdrant defaults, good for <1M vectors

- Hybrid search: dense (embedding) + sparse (BM25) — Qdrant supports both natively

## 8.3 Data Tier Routing

| Tier | Data Type | LLM Route | Storage |
| --- | --- | --- | --- |
| NA (Non-sensitive) | Meeting transcripts, public docs | Claude Sonnet / GPT-4o via API | Qdrant Cloud or managed |
| Amber | Internal strategy docs, financials | Claude Sonnet via API (encrypted in transit) | Self-hosted Qdrant |
| Red (Sensitive) | PII, legal, confidential | Ollama (Llama3/Mistral) on-prem only | On-prem Qdrant in private VPC |

# 9. LLM Cost Model

## 9.1 Per-workflow cost estimate (Meeting Action Item Extractor)

| Step | Model | Est. tokens | Est. cost |
| --- | --- | --- | --- |
| Whisper transcription (60min meeting) | Whisper API | $0.006/min | ~$0.36 |
| Context enrichment (Linear fetch) | N/A (API call) | — | <$0.01 |
| Extraction LLM call (4k context in, 500 out) | Claude Sonnet 4.6 | ~4500 tokens | ~$0.02 |
| Total per meeting | — | — | ~$0.39 |

At 100 meetings/week: ~$39/week → ~$170/month. With WOZCODE optimisation (25–50% reduction): ~$85–130/month. Recoverable at $500+/month org pricing.

## 9.2 Cost Reduction Levers

- WOZCODE: install immediately. 25–50% reduction on Claude Code build costs.

- Whisper self-host: at >100 meetings/day, run Whisper on a $50/month GPU instance to eliminate API cost.

- Prompt caching: Claude Sonnet supports prompt caching on system prompt. Cache the extraction system prompt to reduce input token cost by ~90% on repeat calls.

- Haiku for classification: use claude-haiku-4-5 for data tier classification (fast, cheap). Reserve Sonnet for extraction.

- Batch API: for non-real-time enrichment (e.g., re-indexing old meetings), use Anthropic's batch API at 50% cost.

# 10. Integration Priority

| Integration | Priority | Reason | Via |
| --- | --- | --- | --- |
| Zoom (webhook) | MVP v1 | Core workflow trigger | Zoom Marketplace App + Composio |
| Linear (read + write) | MVP v1 | Ticket creation destination | Composio |
| Slack (write) | MVP v1 | Confirmation message + summary | Composio |
| Google Drive | v1.1 | Onboard existing docs to org brain | Composio (or Airbyte) |
| Notion | v1.1 | MU uses Notion heavily | Composio |
| Gmail | v1.1 | Decision trails in email threads | Composio |
| AWS S3 | v1.2 | Large file ingestion for Madverse | Airbyte |
| Jira | v1.2 | Madverse SaaS pilot alternative to Linear | Composio |

# 11. What NOT to Build for MVP

These are common over-engineering traps. Each costs weeks and zero pilot value.

- A universal connector marketplace — build exactly 3 connectors (Zoom, Linear, Slack)

- A full graph database (Neo4j etc) — start with Qdrant vector search + PostgreSQL relational data

- Multi-tenant role-based access control — one admin per org, one role, build RBAC for v2

- Real-time streaming transcription — batch process after meeting ends is fine for v1

- Airbyte for MVP ingestion — direct Composio connectors are faster to wire and good enough for <10 sources

- Custom embedding model fine-tuning — use text-embedding-3-small, it's good enough

- Self-hosted Whisper — use the API until cost justifies the operational complexity

- A mobile app

- SSO / SAML — email+password for MVP pilot

# 12. Instructions for the Coding Agent

This section is written directly for the coding agent executing this build.

## Environment Setup

- Python 3.11+ for backend. Node 18+ for frontend.

- Use uv (astral-sh/uv) for Python dependency management — faster than pip, lockfile-based.

- Backend repo structure: /api (FastAPI app), /workers (Celery tasks), /ingestion (connectors), /memory (chunk store), /agents (LLM workflows)

- Frontend: existing Next.js repo. Add /app/workflows, /app/integrations routes.

## Critical Implementation Notes

- Composio SDK: use composio-core. Auth via COMPOSIO_API_KEY env var. All OAuth flows go through Composio — do not build OAuth from scratch.

- LiteLLM: always initialise with fallback list: [claude-sonnet-4-6, gpt-4o, ollama/llama3]. Never hardcode a single provider.

- Zoom webhook: verify X-Zoom-Signature-256 header on every request. Fail loudly if invalid. Zoom docs: developers.zoom.us/docs/api/rest/webhook-reference/

- Whisper API: POST to https://api.openai.com/v1/audio/transcriptions with model=whisper-1, response_format=verbose_json to get word-level timestamps.

- Qdrant: use qdrant-client Python SDK. Collection names must be URL-safe (org_<uuid4_hex>).

- Celery: use Redis as both broker and result backend. Chain tasks: download → transcribe → enrich → extract → execute.

- Pydantic v2: define ActionItem, WorkflowRun, MeetingContext as Pydantic models. Validate all LLM outputs against ActionItem schema before execution.

- Async everywhere: FastAPI endpoints must be async def. Celery tasks are sync but use asyncio.run() for async sub-calls.

## Extraction Prompt Template

System prompt (cache-eligible):

You are an operations assistant that extracts action items from meeting transcripts. Return ONLY valid JSON. No preamble. No markdown fences. Schema: [{"title": str, "assignee_email": str¦null, "priority": "urgent"¦"high"¦"medium"¦"low", "due_date": "YYYY-MM-DD"¦null, "context": str}] Rules: Only extract explicit commitments. If no clear owner, set assignee_email to null. Context = 1 sentence explaining why this matters.

## File Structure Reference

osai-backend/ api/ main.py # FastAPI app, router registration routes/ webhooks.py # POST /webhooks/zoom workflows.py # GET /workflows, GET /workflows/{id} integrations.py models/ action_item.py # Pydantic schemas workflow_run.py workers/ tasks.py # Celery tasks chain transcribe.py # Whisper API call extract.py # LiteLLM extraction call execute.py # Composio action calls memory/ chunker.py # LangChain splitter + metadata store.py # Qdrant client wrapper retriever.py # Hybrid search integrations/ composio_client.py # Composio SDK wrapper zoom.py # Zoom webhook signature verify config.py # LiteLLM config, env vars docker-compose.yml # fastapi + pg + redis + qdrant

# 13. Quick Reference — Links

## Open-Source Repos

→ tinyhumansai/openhuman (PRIMARY REFERENCE)

→ onyx-dot-app/onyx

→ BerriAI/litellm

→ WithWoz/wozcode-plugin

→ agiresearch/AIOS

→ ultracontext/ultracontext

## Documentation

→ Composio docs

→ LiteLLM docs

→ Qdrant docs

→ Onyx connector docs

→ OpenHuman docs

→ Zoom webhook reference

→ Whisper API

## Competitor Products

→ Onyx (paid cloud)

→ Glean

→ Viktor

→ memory.store

→ WOZCODE

OSAI MVP Build Brief · May 2026 · Confidential to founding team